## Sheet1
Date | Work
2022-03-04 | Rnd Of Eduport & Configure Laptop for Office work
2022-03-05 | Start reading codes of eduport and learn about basic function of project
2022-03-07 | Start working on HOD dashboard for eduport
2022-03-08 | Added some models and add instructor & update instructor
2022-03-09 | Work on instructor module and added codes related to edit instructor and del instructor
2022-03-11 | work on course price and student module and signup details with hod pannel
2022-03-12 | start working on instructor dashboard and added instructor pannel to dashboard and created some basic function
2022-03-14 | work on edit profile, add course page rendering and profile, showing profile details on every page on instructor pannel(instructor complete)
2022-03-15 | work on student pannel and edit profile, profile, show every data of student on dashboard and connect student signup to student dashborad
2022-03-16 | work on homepage signup, login and profile after that finish student dashboard( brief introduction on job portal)
2022-03-17 | research on job portal and meeting with abhinav sir and kasim about job portal
2022-03-21 | done some rendering templates of job portal and go through of doc ( bandwidth.com )
2022-03-22 | Work on remaining of eduport (instructor added on home page, commented create course,home page profile, course category on home page)
2022-03-23 | Update Edit profile of student,added change password in student pannel & job portal dashboard attached to all its user and differenciate every component of template
2022-03-24 | working on job portal static files and frontend interface, added login and signup form, user dynamic view on admin dashboard, added profile image of admin and added models of admin.
2022-03-25 | added models for admin in job portal and half complete profile of admin and creater new templates for admin profile
2022-03-26 | leave
2022-03-28 | created full profile templates of admin and comapny ,edit and updtae of both admin and company profile (1 issue to be resolved by arman sir)
2022-03-29 | created extra information for company profile and modified ciode in templates
2022-03-30 | working on company dashboard and added fields for information in company profile(help from armaan sir)
2022-03-31
2022-04-01